## Sheet1
Task Description | Start Date
Role Assignment | 2026-01-22 | 0
Client Interview | 2026-01-29 | 0
Website Design Sketches | 2026-01-29 | 7
Create Home Page Layouts | 2026-02-05 | 7
Live Chat | 2026-02-12 | 14
Primary Research (Student Survey) | 2026-02-12 | 14
Weekly Website Testing | 2026-02-12 | 28
Profile Section | 2026-02-12 | 7
Header, Footer, Login, & Donation Pages | 2026-02-12 | 7
Database Setup & Schema | 2026-02-19 | 20
Browse Page (Search & Filters) | 2026-02-19 | 7
FAQ, T&C Pages | 2026-02-19 | 7
LSEPI Documentation | 2026-02-26 | 7
Functional/Non-Functional Requirements | 2026-02-26 | 13
Accessibility & General Settings | 2026-02-26 | 7
About Us, Privacy Policy, & Contact Us | 2026-02-26 | 7
Code Readability & Comments | 2026-03-05 | 7
CSS for Admin Pages | 2026-03-05 | 6
Career Advice & Sign-up Pages | 2026-03-05 | 7
Post Job & Promote Pages | 2026-03-05 | 6